## Comminssioning Table
Factory Acceptance Test- FAT
Installation and operation - Adjustment of the entire system with regard to position & function with the fluidic diagram, only N2
Adjustment of the main components with regard to position with the fluidic diagram
lfd. Nr. | Module | Components | Position (Check of each fluidic component according to P&ID and in correlation to neighbouring components.) |  | Direction (Check connection of pipes and flow direction according to P&ID connected pipes and flow direction.) |  | Electrical Connection |  |  | Pressure test and Leak Test (P = 100 bar max at room temperature Leak rate over 1 hr at < 0.1 bar) |  |  |  | Different devices function Test |  |  |  | Problem / Comment
|  |  | Acceptance |  | Acceptance |  | Method | Acceptance |  | Requirement | Method | Acceptance |  | Requirement | Method | Acceptance
|  |  | Yes | No | Yes | No |  | Yes | No |  |  | Yes | No |  |  | Yes | No
1 | Compressor | C2008 | X |  | X |  | Remove electrical connection of compressors; check assignment via GUI | X |  | 100 bar | Pressurized system with N2 and check leakage | X |  |  | Test compressor under process conditions and check PIZA2009 | X
2 | Check Valves | CV1010 | X |  | X |  | NA |  |  |  | Pressurized system with N2 and check leakage | X |  |  | Pressurized the system and check the back flow from the valve | X
3 |  | CV2105 | X |  | X | [6 empty] | X |  |  |  | X
4 |  | CV2115 | X |  | X | [6 empty] | X |  |  |  | X
5 |  | CV2205 | X |  | X | [6 empty] | X |  |  |  | X
6 |  | CV2215 | X |  | X | [6 empty] | X |  |  |  | X
7 |  | CV2305 | X |  | X | [6 empty] | X |  |  |  | X
8 |  | CV2315 | X |  | X | [6 empty] | X |  |  |  | X
9 |  | CV2405 | X |  | X | [6 empty] | X |  |  |  | X
10 |  | CV2505 | X |  | X | [6 empty] | X |  |  |  | X
11 |  | CV3007 | X |  | X | [6 empty] | X |  |  |  | X
12 |  | CV4006 | X |  | X | [6 empty] | X |  |  |  | X
13 |  | CV5011 | X |  | X | [6 empty] | X |  |  |  | X
14 |  | CV6004 | X |  | X | [6 empty] | X |  |  |  | X
15 |  | CV6012 | X |  | X | [6 empty] | X |  |  |  | X
16 |  | CV7007 | X |  | X | [6 empty] | X |  |  |  | X
17 | Diff. Pressure Sensors | dPIZA1 | X |  | X |  | Connect with electrical power; check assignment via GUI | X |  |  | Pressurized system with N2 and check leakage | X |  |  | Check Procedure in Attachment | X
18 |  | dPIZA2 | X |  | X |  |  | X |  |  |  | X |  |  |  | X
19 |  | dPIZA31 | X |  | X |  |  | X |  |  |  | X |  |  |  | X
20 | Filters | F1006 | X |  | X |  | NA |  |  |  | Pressurized system with N2 and check leakage | X |  |  | Check Procedure in Attachment | X |  | F3001, F4001, F8001, F1006 filter is changed with 60 micro meter
21 |  | F2102 | X |  | X | [6 empty] | X |  |  |  | X
22 |  | F2202 | X |  | X | [6 empty] | X |  |  |  | X
23 |  | F2402 | X |  | X | [6 empty] | X |  |  |  | X
24 |  | F2502 | X |  | X | [6 empty] | X |  |  |  | X
25 |  | F3001 | X |  | X | [6 empty] | X |  |  |  | X
26 |  | F4001 | X |  | X | [6 empty] | X |  |  |  | X
27 |  | F5001 | X |  | X | [6 empty] | X |  |  |  | X
28 |  | F6002 | X |  | X | [6 empty] | X |  |  |  | X
29 |  | F7003 | X |  | X | [6 empty] | X |  |  |  | X
30 |  | F8001 | X |  | X | [6 empty] | X |  |  |  | X
31 | Flow Indicator and Controller | FIC1009 | X |  | X |  | Remove Flow controller connection; check assignment via GUI | X |  |  | Pressurized system with N2 and check leakage | X |  | 13 kg/hr | Test flow with N2 0, 25, 50, 75, 100% flow rate | X
32 |  | FIC2103 | X |  | X |  |  | X |  |  |  | X |  | 10 ln/min |  | X
33 |  | FIC2113 | X |  | X |  |  | X |  |  |  | X |  | 10 ln/min |  | X
34 |  | FIC2203 | X |  | X |  |  | X |  |  |  | X |  | 5 ln/min |  | X
35 |  | FIC2213 | X |  | X |  |  | X |  |  |  | X |  | 5 ln/min |  | X
36 |  | FIC2303 | X |  | X |  |  | X |  |  |  | X |  | 10 ln/min |  | X
37 |  | FIC2403 | X |  | X |  |  | X |  |  |  | X |  | 5 ln/min |  | X
38 |  | FIC2503 | X |  | X |  |  | X |  |  |  | X |  | 5 ln/min |  | X
39 |  | FI6014 | NA |  | NA |  |  | NA |  |  |  | NA |  | NA |  | NA
40 | Fine Regulation Valve | FRV21 | X |  | X |  | NA |  |  |  | Pressurized system with N2 and check leakage | X |  |  | open and closes several times, check function of valve (GUI) | X
41 |  | FRV91 | X |  | X | [6 empty] | X |  |  |  | X
42 |  | FRV2006 | X |  | X | [6 empty] | X |  |  |  | X
43 | Gas Containers | GB2003 | X |  | NA |  | NA |  |  |  | Pressurized system with N2 and check leakage | X |  |  | NA
44 |  | GB2004 | X | [8 empty] | X
45 |  | GB2011 | X | [8 empty] | X
46 | Gas Liquid Separator | GLS5001 | X |  | NA |  | NA |  |  |  | Pressurized system with N2 and check leakage | X |  |  | NA
47 |  | GLS5008 | X | [8 empty] | X
48 |  | GLS6009 | X | [8 empty] | X
49 |  | GLS7001 | X | [8 empty] | X
50 |  | LSV7010 | X | [8 empty] | X
51 | Heating System | HB21 | X |  |  |  | Remove the connector of heating and check the GUI signal | X |  |  | NA |  |  | 300° C | Check Procedure in Attachment | X |  | Heating HB23, HB24, HB25, HB36, HB37, HB38 and HT8012 does not installed
52 |  | HB22 | X |  |  |  |  | X | [7 empty] | X
53 |  | HB23 | NA |  |  |  |  | NA | [7 empty] | NA
54 |  | HB24 | NA |  |  |  |  | NA | [7 empty] | NA
55 |  | HB25 | NA |  |  |  |  | NA | [7 empty] | NA
56 |  | HT4002 | X |  |  |  |  | X | [7 empty] | X
57 |  | HT4012 | X |  |  |  |  | X | [7 empty] | X
58 |  | HT3010 | X |  |  |  |  | X | [5 empty] | 200° C |  | X
59 |  | HB31 | X |  |  |  |  | X | [7 empty] | X
60 |  | HB32 | X |  |  |  |  | X | [7 empty] | X
61 |  | HB33 | X |  |  |  |  | X | [7 empty] | X
62 |  | HB35 | X |  |  |  |  | X | [7 empty] | X
63 |  | HB36 | NA |  |  |  |  | NA | [7 empty] | NA
64 |  | HB37 | NA |  |  |  |  | NA | [7 empty] | NA
65 |  | HB38 | NA |  |  |  |  | NA | [7 empty] | NA
66 |  | HT5002 | X |  |  |  |  | X | [5 empty] | 150° C |  | X
67 |  | HT5008 | X |  |  |  |  | X | [7 empty] | X
68 |  | HT5012 | X |  |  |  |  | X | [5 empty] | 100° C |  | X
69 |  | HB51 | X |  |  |  |  | X | [5 empty] | 150° C |  | X
70 |  | HT6012 | X |  |  |  |  | X | [5 empty] | 300° C |  | X
71 |  | HT8002 | X |  |  |  |  | X | [5 empty] | 200° C |  | X
72 |  | HT8012 | NA |  | NA |  |  | NA | [7 empty] | NA
73 | Heat Exchanger and Coolers | HE3010 | X |  |  |  | NA | X |  |  | Pressurized system with N2 and check leakage |  |  |  | Check Procedure in Attachment | X
74 |  | HE5002 | X |  | X |  |  | X | [7 empty] | X
75 |  | HE5006 | X |  | X |  |  | X | [7 empty] | X
76 |  | HE6007 | X |  | X |  |  | X | [7 empty] | X
77 |  | HE8002 | X |  | X |  |  | X | [7 empty] | X
78 | Pumps | HP1007 | X |  | X |  | Remove electrical connection of pumps; check assignment via GUI | X |  | 20 bar | Pressurized system with N2 and check leakage | X |  |  | Test pump under process conditions and check FIC1009 | X
79 |  | HP3006 | X |  | X |  |  | X |  | 100 bar |  | X |  |  | Test pump under process conditions and check dPIZA1 | X
80 |  | SP5001 | X |  | X |  |  | X |  |  | Pressurized system with N2 and check leakage | X |  |  | Test pump under process conditions and check LICZA5001 | X |  | in SP8004 Had some manufacturing problem, sent back to manufacturer it is returned on 18th March 2020
81 |  | SP8004 | X |  | X |  |  | X |  |  |  | X |  |  | Test pump under process conditions and check dPIZA31 | X
82 | Level Indicators | LICZA1010 | X |  | NA |  | Remove level indicator; check assignment via GUI | X |  |  | Pressurized system with N2 and check leakage | X |  |  | Check Procedure in Attachment | X
83 |  | LICZA1020 | X |  |  |  |  | X |  |  |  | X |  |  |  | X
84 |  | LICZA1120 | X |  |  |  |  | X |  |  |  | X |  |  |  | X
85 |  | LICZA1130 | X |  |  |  |  | X |  |  |  | X |  |  |  | X
86 |  | LICZA21 | X |  |  |  |  | X |  |  |  | X |  |  |  | X
87 |  | LICZA22 | X |  |  |  |  | X |  |  |  | X |  |  |  | X
88 |  | LICZA31 | X |  |  |  |  | X |  |  |  | X |  |  |  | X
89 |  | LICZA32 | X |  |  |  |  | X |  |  |  | X |  |  |  | X
90 |  | LICZA5001 | X |  |  |  |  | X |  |  |  | X |  |  |  | X
91 |  | LICZA5002 | X |  |  |  |  | X |  |  |  | X |  |  |  | X
92 | Multi Port Valves | MPV21 | X |  | X |  | NA |  |  |  | Pressurized system with N2 and check leakage | X |  |  | open and closes several times, check function of valve (GUI) | X
93 |  | MPV91 | X |  | X | [6 empty] | X |  |  |  | X
94 |  | MPV 92 | X |  | X | [6 empty] | X |  |  |  | X
95 | Magnetic Valve | MV1005 | X |  | X |  | Remove Magnetic valve connection; check assignment via GUI | X |  |  | Pressurized system with N2 and check leakage | X |  |  | open and closes several times, check function of valve (GUI) | X
96 |  | MV1015 | X |  | X |  |  | X |  |  |  | X |  |  |  | X
97 |  | MV2004 | X |  | X |  |  | X |  |  |  | X |  |  |  | X
98 |  | MV2005 | X |  | X |  |  | X |  |  |  | X |  |  |  | X
99 |  | MV2012 | X |  | X |  |  | X |  |  |  | X |  |  |  | X
100 |  | MV2104 | X |  | X |  |  | X |  |  |  | X |  |  |  | X
101 |  | MV2114 | X |  | X |  |  | X |  |  |  | X |  |  |  | X
102 |  | MV2204 | X |  | X |  |  | X |  |  |  | X |  |  |  | X
103 |  | MV2214 | X |  | X |  |  | X |  |  |  | X |  |  |  | X
104 |  | MV2304 | X |  | X |  |  | X |  |  |  | X |  |  |  | X
105 |  | MV2314 | X |  | X |  |  | X |  |  |  | X |  |  |  | X
106 |  | MV2404 | X |  | X |  |  | X |  |  |  | X |  |  |  | X
107 |  | MV2504 | X |  | X |  |  | X |  |  |  | X |  |  |  | X
108 | Pressure Control Valves | PCV4005 | X |  | X |  | Remove electrical connection of PCV; check assignment via GUI | X |  |  | Pressurized system with N2 and check leakage |  |  | 100 bar | Check Procedure in Attachment | X |  | At 20% valves are closed and at 100% valves are fully opened
109 |  | PCV6006 | X |  | X |  |  | X | [5 empty] | 100 bar |  | X
110 |  | PCV7002 | X |  | X |  |  | X | [5 empty] | 20 bar |  | X
111 | Pressure Gauge | PG2101 | X |  | NA |  | NA |  |  |  | Pressurized system with N2 and check leakage | X |  |  | Check the needle of the pressure gauge during prussrization | X
112 |  | PG2201 | X | [8 empty] | X |  |  |  | X
113 |  | PG2401 | X | [8 empty] | X |  |  |  | X
114 |  | PG2501 | X | [8 empty] | X |  |  |  | X
115 | Pressure Sensors | PIZA1011 | X |  | NA |  | Remove pressure sensor; check assignment via GUI | X |  | 3 bar | Pressurized system with N2 and check leakage | X |  | 10 bar | Check Procedure in Attachment | X
116 |  | PIZA1014 | X |  |  |  |  | X |  | 20 bar |  | X |  | 20 bar |  | X
117 |  | PIZA2001 | X |  |  |  |  | X |  | 10 bar |  | X |  | 100 bar |  | X
118 |  | PIZA2007 | X |  |  |  |  | X |  | 10 bar |  | X |  | 50 bar |  | X
119 |  | PIZA2009 | X |  |  |  |  | X |  | 100 bar |  | X |  | 1 bar |  | X
120 | Pressure Sensors | PIZA3002 | X |  | NA |  | Remove pressure sensor; check assignment via GUI | X |  | 20 bar | Pressurized system with N2 and check leakage | X |  | 10 bar | Check Procedure in Attachment | X
121 |  | PIZA3010 | X |  |  |  |  | X |  | 100 bar |  | X |  | 100 bar |  | X
122 |  | PI4004 | X |  |  |  |  | X |  | 100 bar |  | X |  | 100 bar |  | X
123 |  | PI4005 | X |  |  |  |  | X |  | 50 bar |  | X |  | 3 bar |  | X
124 |  | PIC6003 | X |  |  |  |  | X |  | 100 bar |  | X |  | 100 bar |  | X
125 |  | PIZA8005 | X |  |  |  |  | X |  | 1 bar |  | X |  | 20 bar |  | X
126 | Containers | SL1001 | X |  | NA |  | NA |  |  |  | Pressurized system with N2 and check leakage | X |  | Filling | Fill with Fluid, check level sensor via GUI | X
127 |  | SL5009 | X | [8 empty] | X |  | Filling |  | X
128 | Pressure Relief Valve | SRV1003 | X |  | X |  | NA |  |  |  | Pressurized system with N2 and check leakage | X |  | 2 bar | Check Procedure in Attachment | X
129 |  | SRV1008 | X |  | X | [6 empty] | X |  | 20 bar |  | X
130 |  | SRV2010 | X |  | X | [6 empty] | X |  | 102 bar |  | X
131 | Thermo Couples | TI11 | X |  | NA |  | Remove thermocouple; check assignment via GUI | X |  |  | Pressurized system with N2 and check leakage |  |  |  | Check Procedure in Attachment | X |  | Checked at room temperature
132 |  | TI12 | X |  |  |  |  | X | [7 empty] | X
133 |  | TIZA2011 | X |  |  |  |  | X | [7 empty] | X
134 |  | TIC21 | X |  |  |  |  | X | [7 empty] | X
135 |  | TIZA22 | X |  |  |  |  | X | [7 empty] | X
136 |  | TIC23 | X |  |  |  |  | X | [7 empty] | X
137 |  | TIZA24 | X |  |  |  |  | X | [7 empty] | X
138 |  | TIC25 | X |  |  |  |  | X | [7 empty] | X
139 |  | TIZA26 | X |  |  |  |  | X | [7 empty] | X
140 |  | TIC27 | X |  |  |  |  | X | [7 empty] | X
141 |  | TIZA28 | X |  |  |  |  | X | [7 empty] | X
142 |  | TIC29 | X |  |  |  |  | X | [7 empty] | X
143 |  | TIZA30 | X |  |  |  |  | X | [7 empty] | X
144 |  | TI3003 | X |  |  |  |  | X | [7 empty] | X
145 |  | TIC3009 | X |  |  |  |  | X | [7 empty] | X
146 |  | TIZA3010 | X |  |  |  |  | X | [7 empty] | X
147 |  | TIC31 | X |  |  |  |  | X | [7 empty] | X
148 |  | TIZA32 | X |  |  |  |  | X | [7 empty] | X
149 |  | TIC33 | X |  |  |  |  | X | [7 empty] | X
150 |  | TIZA34 | X |  |  |  |  | X | [7 empty] | X
151 |  | TIC35 | X |  |  |  |  | X | [7 empty] | X
152 |  | TIZA36 | X |  |  |  |  | X | [7 empty] | X
153 |  | TIC37 | X |  |  |  |  | X | [7 empty] | X
154 |  | TIZA38 | X |  |  |  |  | X | [7 empty] | X
155 |  | TIC39 | X |  |  |  |  | X | [7 empty] | X
156 |  | TIZA40 | X |  |  |  |  | X | [7 empty] | X
157 |  | TIC4001 | X |  |  |  |  | X | [7 empty] | X
158 |  | TIZA4002 | X |  |  |  |  | X | [7 empty] | X
159 |  | TI4003 | X |  |  |  |  | X | [7 empty] | X
160 |  | TIC4011 | X |  |  |  |  | X | [7 empty] | X
161 |  | TIC41 | X |  |  |  |  | X | [7 empty] | X
162 |  | TIZA42 | X |  |  |  |  | X | [7 empty] | X
163 |  | TIC43 | X |  |  |  |  | X | [7 empty] | X
164 |  | TIZA44 | X |  |  |  |  | X | [7 empty] | X
165 |  | TI45 | X |  |  |  |  | X | [7 empty] | X
166 |  | TIC5001 | X |  |  |  |  | X | [7 empty] | X
167 |  | TIZA5002 | X |  |  |  |  | X | [7 empty] | X
168 | Thermo Couples | TIZA5004 | X |  | NA |  | Remove thermocouple; check assignment via GUI | X |  |  | Pressurized system with N2 and check leakage |  |  |  | Check Procedure in Attachment | X |  | Checked at room temperature
169 |  | TI5005 | X |  |  |  |  | X | [7 empty] | X
170 |  | TIC5007 | X |  |  |  |  | X | [7 empty] | X
171 |  | TIZA5008 | X |  |  |  |  | X | [7 empty] | X
172 |  | TIC5009 | X |  |  |  |  | X | [7 empty] | X
173 |  | TIZA5010 | X |  |  |  |  | X | [7 empty] | X
174 |  | TIC5011 | X |  |  |  |  | X | [7 empty] | X
175 |  | TIZA5012 | X |  |  |  |  | X | [7 empty] | X
176 |  | TIZA5014 | X |  |  |  |  | X | [7 empty] | X
177 |  | TIC6011 | X |  |  |  |  | X | [7 empty] | X
178 |  | TIZA6012 | X |  |  |  |  | X | [7 empty] | X
179 |  | TIZA6013 | X |  |  |  |  | X | [7 empty] | X
180 |  | TIZA7004 | X |  |  |  |  | X | [7 empty] | X
181 |  | TIZA7006 | X |  |  |  |  | X | [7 empty] | X
182 |  | TIC8001 | X |  |  |  |  | X | [7 empty] | X
183 |  | TIZA8002 | X |  |  |  |  | X | [7 empty] | X
184 |  | TIZA8003 | X |  |  |  |  | X | [7 empty] | X
185 |  | TIZA8008 | X |  |  |  |  | X | [7 empty] | X
186 |  | TIC8011 | X |  |  |  |  | X | [7 empty] | X
187 |  | TIZA8012 | X |  |  |  |  | X | [7 empty] | X
188 | Three way Valve | TWV5013 | X |  | X |  | NA |  |  |  | Pressurized system with N2 and check leakage | X |  |  | open and closes several times, check function of valve (GUI) | X
189 |  | TWV6001 | X |  | X | [6 empty] | X |  |  |  | X
190 |  | TWV6013 | X |  | X | [6 empty] | X |  |  |  | X
191 |  | TWV7009 | X |  | X | [6 empty] | X |  |  |  | X
192 |  | TWV8006 | X |  | X | [6 empty] | X |  |  |  | X
193 |  | TWV8007 | X |  | X | [6 empty] | X |  |  |  | X
194 | Valves | V1001 | X |  | X |  | NA |  |  |  | Pressurized system with N2 and check leakage | X |  |  | open and closes several times, check function of valve (GUI) | X
195 |  | V1004 | X |  | X | [6 empty] | X |  |  |  | X
196 |  | V1012 | X |  | X | [6 empty] | X |  |  |  | X
197 |  | V2101 | X |  | X | [6 empty] | X |  |  |  | X
198 |  | V2201 | X |  | X | [6 empty] | X |  |  |  | X
199 |  | V2401 | X |  | X | [6 empty] | X |  |  |  | X
200 |  | V2501 | X |  | X | [6 empty] | X |  |  |  | X
201 |  | V6011 | X |  | X | [6 empty] | X |  |  |  | X
202 |  | V6012 | X |  | X | [6 empty] | X |  |  |  | X
203 |  | V7005 | X |  | X | [6 empty] | X |  |  |  | X
204 |  | V7006 | X |  | X | [6 empty] | X |  |  |  | X
205 |  | V7010 | X |  | X | [6 empty] | X |  |  |  | X
206 | Alarms | Gas Alarm (VSI3) | X |  | NA |  | Remove Electrical Wiring; check assignment via GUI | X |  |  |  | NA |  |  | Check the behaviour of every alarm sensors | X
207 |  | Thermo Couple | X |  | NA |  |  | X |  |  |  | NA |  |  |  | X
208 |  | Pressure Sensors | X |  | NA |  |  | X |  |  |  | NA |  |  |  | X
209 |  | Ventilation | X |  | NA |  |  | X |  |  |  | NA |  |  |  | X
210 |  | Flamable Gas (GSII) | X |  | NA |  |  | X |  |  |  | NA |  |  |  | X
| Further open points/problems | [7 empty] | Solution Approach
214 | In Washing column 5 kg ceramic material is insterted and column is closed with pressure test of 14 bar.
215 | In Rectification column 5 kg ceramic material is insterted and column is leak tested but without original heating sealing.
216
217

## Procedure Sheet
Factory Acceptance Test
lfd No. | Devices | Function test | Acceptance
|  |  | Yes | No
Compressor
1 | C2008 | Check Direction and Postion as per P&ID diagram. | X
Check Valves
2 | All Check Valves | Check Direction and Postion as per P&ID diagram . | X
differential Pressure Sensors
3 | dPIZA1 | Fill up the washing column with liquid check out the level indicator LICZA1120 and LICZA1130. Measure the height and calculate the differential pressure. | X
4 | dPIZA2 | Fill up the reactor check out the level indicator LICZA22 and LICZA21. Measure the height and calculate the differential pressure. | X
5 | dPIZA31 | Fill up the distillation column check out the level indicator LICZA31 and LICZA32. Measure the height and calculate the differential pressure. | X
Filters
6 | All Filters | Check Position and Direction of filters as per P&ID diagram. | X
Flow Conroller and Indicator
7 | All Flow cotroller & Indicator | Check Position and Direction of flow controller and Indicator as per P&ID diagram. | X
Fine Regulation Valve
8 | All Fine Regulation Valve | Check Position and Direction of fine regulation valve as per P&ID diagram. | X
Gas Container
9 | All Gas Containers | Check Positon of all gas containers as per P&ID diagram. | X
Gas Liquid Separator
10 | All Gas Liquid Separator | Check Positon of all gas liquid separator as per P&ID diagram. | X
Heating System
11 | HB21 | Heat up the system HB21 up to 300° C, check the temperature on TIZA22. | X
12 | HB22 | Heat up the system HB22 up to 300° C, check the temperature on TIZA24. | X
13 | HB23 | Heat up the system HB23 up to 300° C, check the temperature on TIZA26. | X
14 | HB24 | Heat up the system HB24 up to 300° C, check the temperature on TIZA28. | X
15 | HB25 | Heat up the system HB25 up to 300° C, check the temperature on TIZA30. | X
16 | HT3010 | Heat up the system HT3010 up to 200° C, check the temperature on TIZA3010. | X
17 | HB31 | Heat up the system HB31 up to 200° C, check the temperature on TIZA32. | X
18 | HB32 | Heat up the system HB32 up to 200° C, check the temperature on TIZA34. | X
19 | HB33 | Heat up the system HB33 up to 200° C, check the temperature on TIZA36. | X
20 | HB35 | Heat up the system HB35 up to 200° C, check the temperature on TIZA38. | X
21 | HB36 | Heat up the system HB36 up to 200° C, check the temperature on TIZA40. | X
22 | HB37 | Heat up the system HB37 up to 200° C, check the temperature on TIZA42. | X
23 | HB38 | Heat up the system HB38 up to 200° C, check the temperature on TIZA44. | X
24 | HT4002 | Heat up the system HT4002 up to 300° C, check the temperature on TIZA4002. | X
25 | HT4012 | Heat up the system HT4012 up to 300° C, check the temperature on TIZA4012. | X
26 | HT5002 | Heat up the system HT5002 up to 150° C, check the temperature on TIZA5002 | X
27 | HT5008 | Heat up the system HT5008 up to 150° C, check the temperature on TIZA5008. | X
28 | HT5012 | Heat up the system HT5012 up to 150° C, check the temperature on TIZA5012. | X
29 | HB51 | Heat up the system HB51 up to 150° C, check the temperature on TIZA5010. | X
30 | HT6012 | Heat up the system HT6012 up to 300° C, check the temperature on TIZA6012. | X
31 | HT8002 | Heat up the system HT8002 up to 200° C, check the temperature on TIZA8002. | X
32 | HT8012 | Heat up the system HT8012 up to 200° C, check the temperature on TIZA8012. | X
Heat Exchanger and coolers
33 | HE3010 | Heat up HE3010 with outlet of D31 and check the temperature at TI3003 | X
34 | HE5002 | Enter the cold water in HE5002, check the outlet temperature of water at TIZA5004 and check the temperature of HE5002 at TI5005. | X
35 | HE5006 | Enter the cold water in HE5006 and check the outlet temperature of water at TIZA5014. | X
36 | HE6007 | Enter the cold water in HE6007 and check the outlet temperature of water at TIZA6013. | X
37 | HE8002 | Enter the cold water in HE8002, check the outlet temperature of water at TIZA8008 and check the temperature of HE8002 at TI8003. | X
Pumps
38 | All Pumps | Check position according to P&ID diagram and test pump under conditions. | X
Level Indicator
39 | LICZA1010, LICZA1020 | Fill up SL1001 with Liquid and check the function of LICZA1010 and LICZA1020. | X
40 | LICZA1120, LICZA1130 | Fill up WC1 and check the function of LICZA1120 and LICZA1130. | X
41 | LICZA5001, LICZA5002 | Fill up GLS5001 and check the function of LICZA5001 and LICZA5002. | X
42 | LICZA21, LICZA22 | Test R2 and check the function of LICZA21 and LICZA22. | X
43 | LICZA31, LICZA32 | Test D31 and check the function of LICZA31 and LICZA32. | X
Multi Port Valves
44 | All Multi Port Valves | Check position and directions of MPV as per P&ID diagram. | X
Magnetic Valve
45 | All Magnetic Valves | Check position and directions of magnetic valves as per P&ID diagram. | X
Pressure Control Valves
46 | PCV4005 | Pressurized the system with liquid from reactor outlet till CV4004 at 100 bars. Close reactor outlet and CV4004 and check the pressure on PI4004. | X
47 | PCV6006 | Pressurized the system with gas from TWV6001 till V6011 at 100 bars. Close TWV6001 and V6011 and check the pressure on PIC6003. | X
48 | PCV7002 | Pressurized the system with gas from Washing Column exhaust gas outlet till V7005 at 20 bars. Close Washing Column exhaust gas outlet and V7005 and check the pressure on PIZA1011. | X
Pressure Sensors (Connect Pressure sensors with External Pressure indicator)
49 | PIZA1011 | Pressurize system from MV1004 till Washing Column Inlet at 3 bar. Close the valve MV1004 and Washing column inlet. Check the pressure at PIZA1011. | X
50 | PIZA1014 | Pressurize system from V2201 till SRV1003 at 20 bar. Close the V2201 and SRV1003. Check the pressure at PIZA1014. | X
51 | PIZA2001 | Pressurize system from V2401, V2201 and V2501 till Mix 2002 at 10 bar. Close V2401, V2501 and V2201 and Mix 2002. Check the pressure at PIZA2001. | X
52 | PIZA2007 | Pressurize system from V2201 and V2101 till C2008 inlet at 10 bar. Close V2201, V2101 and C2008 inlet. Check the pressure at PIZA2007. | X
53 | PIZA2009 | Pressurize system from V2201 and V2101 till GB2004 inlet at 100 bar. Close V2201, V2101 and V2101 inlet. Check the pressure at PIZA2007. | X
54 | PIZA3002 | Pressurize system from washing column outlet till HP3006 at 20 bar. Close the Washing Column outlet and HP3006. Check the pressure at PIZA3002. | X
55 | PIZA3010 | Pressurize system from washing column outlet till Reactor Inlet at 100 bar. Close the Washing Column outlet and Reactor Inlet. Check the pressure at PIZA3010. | X
56 | PI4004 | Pressurize system from Reactor outlet till PCV4005 at 100 bar. Close the Reactor outlet and PCV4005. Check the pressure at PI4004. | X
57 | PI4005 | Pressurize system from Reactor outlet till Distillation Column inlet at 50 bar. Close the Reactor outlet and Distillation Column inlet. Check the pressure at PI4005. | X
58 | PIC6003 | Pressurized system from TWV6001 till V6011 at 100 bars. Close TWV6001 and V6011 and check the pressure on PIC6003. | X
59 | PIZA8005 | Pressurize system from Distillation Column outlet till V1012 inlet at 1 bar. Close the Reactor outlet and Distillation Column inlet. Check the pressure at PIZA8005. | X
Container
60 | All containers | Check the position of all containers as per P&ID diagram. | X
Pressure Relief Valve
61 | SRV1003 | Pressurized SRV1003 up to 2 bars with external system. Check the pressure on external pressure indicator. | X
62 | SRV1008 | Pressurized SRV1008 up to 20 bars with external system. Check the pressure on external pressure indicator. | X
63 | SRV2010 | Pressurized SRV2010 up to 100 bars with external system. Check the pressure on external pressure indicator. | X
Thermo Couple
64 | All Thermo couple | Check of all indicators at room temperature: Reasonable values, No deviations between temperature indicators. Heating of reactor block up to 300 °C and other heating up to 200 °C: All temperature indicators should have same value ± 3 K. | X
Thre Way Valve
65 | All Three Way Valves | Check the position and direcction of all three way valve as per P&ID diagram. | X
Valves
66 | All Valves | Check the position and direcction of all valve as per P&ID diagram. | X